## Sheet1
| Term 1 | [27 empty] | Holiday | [13 empty] | Term 2
| Week 6 | [6 empty] | Week 7 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Documentation | bar: Week 6 M to Week 1 W; Week 8 M to Week 8 S
Identifying And Defining | bar: Week 6 M to Week 7 S
Research And Planning | bar: Week 7 S to Week 10 W
System Design | bar: Week 10 T to Week 1 W
Producing And Implementing | bar: Week 8 M to Week 8 S
Testing And Evaluation | bar: Week 8 M to Week 8 S
Feedback, Security and Reflection | bar: Week 8 M to Week 8 S
Sprint 1 - Core Mechanics | bar: Week 2 T to Week 2 W
Unity Setup | bar: Week 2 T to Week 2 W
Camera | bar: Week 2 T
Player Character | bar: Week 2 F to Week 2 S
Movement | bar: Week 2 S to Week 1 T
Collision | bar: Week 1 W to Week 1 T
World | bar: Week 1 F to Week 1 S
UI | bar: Week 1 S to Week 2 M
Bug Fix and Testing | bar: Week 2 T to Week 2 W
Sprint 2 - Survival Systems | bar: Week 2 T to Week 4 S
Health System | bar: Week 2 T to Week 2 S
Heath UI | bar: Week 2 S to Week 3 M
Resource Collection | bar: Week 3 T to Week 3 T
Inventory | bar: Week 3 F to Week 3 S
Inventory UI | bar: Week 4 M to Week 4 T
Item Usage | bar: Week 4 W to Week 4 T
Bug Fix and Testing | bar: Week 4 F to Week 4 S
Sprint 3 - Enemies | bar: Week 4 S to Week 7 T
Enemy Creation | bar: Week 4 S to Week 5 M
Enemy Behaviour | bar: Week 5 T to Week 5 F
Damage System | bar: Week 5 S to Week 5 S
Combat System | bar: Week 6 M to Week 6 W
Enemy Spawning | bar: Week 6 T to Week 6 F
Hunger | bar: Week 6 S to Week 6 S
Bug Fix and Testing | bar: Week 7 M to Week 7 T
Sprint 4 - Additional Features | bar: Week 7 W to Week 8 S
Sound (Effects and Background) | bar: Week 7 W to Week 7 F
Main and Pause Menu | bar: Week 7 S to Week 7 S
Story | bar: Week 8 M to Week 8 F
Bug Fix and Testing | bar: Week 8 S to Week 8 S